## Cover
Guidance on Providing Benefits and Business Case Info

	This template provides guidance on the inputs we require as part of the wider Programme Business Case process. These inputs will also be required as part of the economic case appraisal for the business case you submit.
	We understand that all projects are at an early stage, and all inputs will be estimates based on best efforts and available data. You are encouraged to provide your best estimate and iterate as you find more data.
	To allow this iteration, we are asking for data in three tranches:
		1st tranche by 8th March: Any data you have already.
		2nd tranche by 22nd March: Data from initial research and estimates
		3rd tranche for submission with business case: Data accompanying and substantiating business case assessment

Instructions
-	This template provides guidance on providing MHCLG with inputs on your project benefits, and guidance on calculating the costs and benefits of your project as part of the business case development process.
-	Please complete as much of the 'Model Input' sheet as possible, with appropriate notes for sources and calculation methodology.
-	Important inputs are highlighted in red, so focus on these.
-	Please make use of notes and add supplementary info to explain your calculations and sources in the 'Detailed working' tab.
-	Please focus on benefits and costs to public sector organisations, particularly to local authorities. Where you include costs and benefits to citizens, private sector etc, please show this in the breakdown.
-	You can use these inputs to create your economic appraisal as part of your business case, as in the 'Example appraisal' sheet.
-	Inputs are requested for participating councils as well as an estimate for the 'average UK council' that might deploy this service. In many cases, you may need to assume similar parameters between these categories.
-	Please send any supporting documentation.

Tips for completing this template
-	Given the lack of data on projects that are still in development, please make assumptions based on suitable evidence - similar systems, historical examples and expert advice.
-	Use the GDS Benefits Handbook for reference assumptions, e.g. on staff costs and transactions costs. These should be adjusted for your circumstances where necessary.
-	Where a new service will reduce an existing cost base (e.g. digitising an analog service, reducing manual entry), make a conservative assumption on what % of costs could be avoided using a reference point.
-	Make use of examples of benefits that have already been achieved in similar areas.

Disclaimer
	This confidential model has been prepared solely for information purposes, and is available to a limited number of parties solely to assist the recipient in exploring options around the project. / We reserve the right to amend or replace the model at any time. Although we may provide additional information to interested parties concerning the project, we are not under any obligation to update, keep current, or correct the information contained in this model or to provide any additional information. Interested parties should conduct their own investigation and analysis of the project. This model contains information from third parties and neither such information nor this model has been independently verified. Recipients are solely responsible for performing their own due diligence to verify for themselves the adequacy, accuracy and completeness of the information and the model. Neither us nor any of our respective directors, employees, affiliates or agents makes any representation or warranty, express or implied, as to the accuracy, completeness or fairness of the model nor any information provided in connection with it, and none of such parties shall have any liability for the accuracy of or information contained in, or for any omissions from, the financial model, nor for any of the written, electronic or oral communications transmitted to the recipient in the course of the recipient's own investigations and evaluations. / All rights, including-intellectual property rights, in the model belong exclusively to the authors.

## Meta input
Project:	Family Context in Children's Services

Lead Council:	Stockport Metropolitan Borough Council

Contibutors:	Leeds City Council, MHCLG, and Social Finance

Date Completed:	20/5/2019

## Main input
Benefits Capture Template				For Completion
Please complete in £ or % figures as appropriate. See Cover page for instructions			Example category breakdown / Change/add rows as necessary	For lead council	For partners / (average or individual)	For average council	Notes
Variable net benefits
	Annual variable benefits		Total	£258,007		£321,920	see product benefits tab
		In this category we want benefits from providing the service which increase with digital uptake.	Savings from social workers not having to spend time chasing information	£90,481		£112,895	see product benefits tab
			Savings from children and families not escalating unnecessarily	£167,526		£209,025	see product benefits tab

	Annual variable costs		Total
		Change in running costs that vary depending on digital uptake.

	Projected growth rate in demand
	What do you expect to happen to demand for this service?		Demand driver e.g. pressure on children's services

Fixed net benefits
	Annual fixed benefits		Total	£0		£0
		Benefits that arise from delivering the service, regardless of uptake by users	e.g. reduced software licence fees

	Annual fixed costs		Total	£0		£0
		Change in annual overheads that arise from delivering the service, regardless of uptake by users	e.g. Staff Cost
		E.g. core staff time, maintenance, capital and equipment, training, marketing	e.g. Capital and Equipment
			e.g. Training
			e.g. Marketing
Development and delivery costs
	Development and delivery cost		Total			£1,934,314	see cost assumptions tab
		Expected cost of developing project through to live service	Discovery	same as for avg. council		£100,000	see cost assumptions tab
		E.g. staff costs for developing alpha, beta and live service	Alpha	same as for avg. council		£170,000	see cost assumptions tab
			Beta	same as for avg. council		£1,511,814	see cost assumptions tab
			Setup costs for local authorities post beta			£152,500	see cost assumptions tab

	Effect of project (as %)		Total			£188,195
		How much higher is development cost for the lead council compared to a noncollaborative project?	Family Context Setup Costs (one-off, per council)	same as for avg. council		£161,295	one-off cost see cost assumptions tab
		How much lower will it be for the average council that reuses project outputs? E.g. lower development time	Ongoing Product Development and Maintenance Costs (annual, per council)	same as for avg. council		£22,534	on-going cost see cost assumption tab
			Integrating Additional Datasets into Family Context Avg. Per Dataset	same as for avg. council		£4,366	one-off cost see cost assumptions tab
Renewal costs
	Refresh/renewal costs		Total			£39,620	see cost assumptions
		What semi-regular costs will be expected for renewing the service?	Product Development and Maintenance Costs (Beyond MVP)	same as for avg. council		£33,113	see cost assumptions
		E.g. cost of renewing contract, cost of further development time for refresh.	On-going Family Matching Algorithm Cost	same as for avg. council		£2,000	see cost assumptions
			Cost of Collaboration	same as for avg. council		£4,507	see cost assumptions

	Effect of project on renewal cost		Total		[VERY IMPORTANT!]
		What is effect of the project on cost of renewal?	e.g. lower procurement cost
		E.g. lower supplier costs, lower procurement costs

	Frequency of renewal		Total
		How often is this service renewed?				yearly	the service will run yearly with the majority of costs covering local authority time, hosting, further development and implementation of learnings, etc
		E.g. existing contract length, time between redevelopment initiatives
Number of councils
	Number of councils in UK that are willing and able to adopt this service		Total
		Number of councils where this service could apply (i.e. they operate similar systems)				152	use case applies to all councils
		Number of councils that have indicated interested in this project				10	based on workshop with 12 local authorities
		Number of councils that will adopt per year				5	average per year

Any other Costs and Benefits
	Please provide any other quantifiable costs and benefits that you see as relevant to the calculation of net benefits for this project

## Example appraisal
Example Appraisal for Business Case
Where project is replacing another service, this should be in the baseline so costs and benefits are relative to this existing system					All figures in pounds
		19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	Note

For Lead Council only
	Development and delivery costs	-200,000
	Annual fixed costs		-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000
	Annual variable costs		-1,000	-2,000	-4,000	-8,000	-16,000	-16,000	-16,000	-16,000	-16,000	-16,000	-16,000
	Annual fixed benefit		0	0	0	0	0	0	0	0
	Annual variable benefit		20,000	40,000	80,000	160,000	320,000	320,000	320,000	320,000	320,000	320,000	320,000
	Renewal costs					-100,000					-100,000
	Net benefit	-200,000	9,000	28,000	66,000	142,000	294,000	194,000	294,000	294,000	294,000	294,000	194,000
	Discount factor	1.00	0.97	0.93	0.90	0.87	0.84	0.81	0.79	0.76	0.73	0.71	0.68
	Net Present Value	-200,000	8,696	26,138	59,528	123,745	247,540	157,819	231,081	223,267	215,717	208,422	132,879
	TOTAL NPV	1,434,833

Need to adjust for partners and for average council to calculate net benefits from scaling

For average partner council
	Development and delivery costs	-66,667
	Annual fixed costs		-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000
	Annual variable costs		-2,000	-4,000	-8,000	-16,000	-32,000	-32,000	-32,000	-32,000	-32,000	-32,000	-32,000
	Annual fixed benefit		0	0	0	0	0	0	0	0
	Annual variable benefit		10,000	20,000	40,000	80,000	160,000	160,000	160,000	160,000	160,000	160,000	160,000
	Renewal costs					-100,000					-100,000
	Net benefit	-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000	118,000	118,000	118,000	18,000
	Discount factor	1.00	0.97	0.93	0.90	0.87	0.84	0.81	0.79	0.76	0.73	0.71	0.68
	Net Present Value	-66,667	-1,932	5,601	19,843	47,058	99,353	14,643	92,747	89,611	86,580	83,652	12,329
	TOTAL NPV	482,818

For average UK council (where relevant)
	Development and delivery costs	-66,667
	Annual fixed costs		-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000	-10,000
	Annual variable costs		-2,000	-4,000	-8,000	-16,000	-32,000	-32,000	-32,000	-32,000	-32,000	-32,000	-32,000
	Annual fixed benefit		0	0	0	0	0	0	0	0
	Annual variable benefit		10,000	20,000	40,000	80,000	160,000	160,000	160,000	160,000	160,000	160,000	160,000
	Renewal costs					-100,000					-100,000
	Net benefit	-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000	118,000	118,000	118,000	18,000
	Discount factor	1.00	0.97	0.93	0.90	0.87	0.84	0.81	0.79	0.76	0.73	0.71	0.68
	Net Present Value	-66,667	-1,932	5,601	19,843	47,058	99,353	14,643	92,747	89,611	86,580	83,652	12,329
	TOTAL NPV	482,818

Other UK councils by cohort
	Number of councils adopting by cohort
	1st		10
	2nd		0	10
	3rd			0	10
	4th				0	10
	5th					0	10
	Net benefits per council by cohort
	1st		-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000	118,000	118,000	118,000
	2nd			-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000	118,000	118,000
	3rd				-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000	118,000
	4th					-66,667	-2,000	6,000	22,000	54,000	118,000	18,000	118,000
	5th					-66,667	-2,000	6,000	22,000	54,000	118,000	18,000
	NPV by cohort
	1st	4,545,784
	2nd	3,611,158
	3rd	2,708,137
	4th	1,835,653
	5th	992,674

NPV total
		Number	NPV
	Lead council	1	1,434,833
	Partners	3	1,448,453
	Other relevant UK councils		13,693,406
	NPV total		16,576,692

Scenarios		NPV (19/20-30/31)
	Lead council only	1,434,833
	Lead and partners	2,883,286
	All relevant UK councils	16,576,692

## Detailed working
Supporting information
Please provide supplementary info and calculations for your inputs.

## Product benefits
	Benefits of the solution

	Colour code
	Inputs
	Outputs

	SUMMARY OF BENEFITS

	Overall Benefits	Stockport	Leeds	Average Council	Nationwide
1	Savings from social workers not having to spend time chasing information	£150,802	£509,465	£188,159	£28,600,100
2	Savings from children and families not escalating unnecessarily	£279,210	£943,271	£348,374	£52,952,913
	Per annum cost savings from FC	£430,012	£1,452,737	£536,533	£81,553,013

3	Per annum long term cost of care leavers	£4,845,449	£16,369,686	£6,045,746	£918,953,423

	Confidence factors
	Family Context confidence factor - Confidence level	60.00%	Note: We applied a 60% confidence factor to all our benefit assumptions to take into consideration optimism bias. We derived it by applying Greenbook / GDS guidance to findings from user research.

	Benefits included in Benefit Analysis (Discounted w/ confidence factors above)

	Overall Benefits (Discounted)	Stockport	Leeds	Average Council	Nationwide
1	Savings from social workers not having to spend time chasing information	£90,481.41	£305,679.03	£112,895.13	£17,160,060.05
2	Savings from children and families not escalating unnecessarily	£167,525.79	£565,962.87	£209,024.65	£31,771,747.55

1	COST SAVINGS FROM TIME SPENT RESEARCHING

	DESCRIPTION
	Argument: Currently Social Workers are wasting a lot of time trying to find information on family members. With FC, CS will have access to key information on services involved with families and will be able to connect with other services much quicker. This means that Social Workers will be able to save time and spend more time supporting the family.
	Summary of calculation: Impact = Time saved with FC * Average nr of assessments per year * SW cost per hour

	ASSUMPTIONS
	Social Worker Wage (per hour) - Based on Stockport Social Worker costs
	Number of SW assessments per year - Based on Stockport and Leeds figures
	Average nr of hours spent researching per case without FC - Directly asked to Social Workers from Leeds and Stockport during User research
	Average nr of hours spent researching per case with FC - Directly asked to Social Workers from Leeds and Stockport during User research

	Calculations	Stockport	Leeds	Average Council

	Volume & Cost
	Social Worker Wage (per hour)	£21.81	£21.81	£21.81	Source: Stockport Social Worker day rates, assuming a 37.5 hour working week
	Number of SW assessments per year	3,457	11,679	4,313	Source: Characteristics_of_children_in_need_2017-18 by DfE

	Time spent researching
	Average nr of hours spent researching per case without tool	2.5	2.5	2.5	Source: FC User Research
	Percentage of time saved per case with tool	80%	80%	80%	Source: FC User Research

	Savings
	Hours saved by using the tool	2	2	2
	Cost savings from using with tool	£150,802	£509,465	£188,159

2	COST SAVINGS FROM INTERVENING EARLY

	DESCRIPTION
	Argument: Currently, some children are assessed by children's services (CS) but don't get the right level of support because CS don’t have the full picture i.e. the social work assessments results in a "false negative". With FC, CS will have a fuller picture and be able to connect with other services, so they can give the right support. This means that councils can provide support earlier, stopping needs escalating (i.e. it will enable them to "shift to the left"). For a child who, without FC, would have got no support at first referral then moved on to a CPP. Now they will get support at CiN at first referral so their needs are managed here.
	Calculation: Impact = number of false negative assessments currently * proportion we could fix * impact of fixing them

	ASSUMPTIONS
	Number of false negative assesments - a proxy for this is the number of cases that are referred to children's services, no action is taken, but that they are re-referred within a year and social worker involvement is then needed. This is overall likely an underestimate as it is only one way that false negatives are realised (i.e. it requires a re-referral to be made and also requires this to fall into the next calendar year exactly), however has some overestimate as some of these cases will have been correct assessments where the child's needs have genuinely escalated signifcantly over the last years
	Proportion that FC would fix - assumption to be tested in Beta
	Impact of early intervention - assume that if a child that get's the right support the first time, then they can have a lower level of support as their needs are managed. E.g. if previously a child got no support then escalated to CPP, now they will be supported as CiN instead

	Key Assumption
	What proportion of cases which don’t get the right support first time will be improved by Family Context?	20.0%	Assumption to be tested in Beta
	Number of children annualy who don't get right support first time	23,000	Source: Action for Children: The Revolving Door.

		Nationwide	Average Council
	Total annual benefit	£52,952,913	£348,374

	Population that Family Context would help
	Number of children annualy who don't get right support first time	23,000
	What proportion of cases which don’t get the right support first time will be improved by Family Context?	20%
	Total cases Family Context would improve	4,600

	Impact of helping these children
	If child previously would have gone to:	Proportion of cases	Cost of providing support	Cost of this outcome with early intervention	Net benefit per child	Note
	CiN	80%	£10,776	£2,601	£8,175
	CPP	14%	£10,776	£10,776	£-	conservative estimate on potential savings from a child moving from CPP to CiN
	LAC	6%	£44,647	£10,776	£78,518

	Other Inputs

	Number of new cases per annum:
	CiN	406,400	Source: Characteristics_of_children_in_need_2017-18 by DfE - Year 2018
	CPP	68,770	Source: Characteristics_of_children_in_need_2017-18 by DfE - Year 2018
	LAC	32,050	Source: Characteristics looked after in England National Tables - Year 2018

	Average cost in a year of:
	EH	£2,601	Estimated based on the step change in costs between LAC and CPP/CIN
	CiN	£10,776	Source: DfE Aldaba Document, note: 1) this dataset combines CiN and CPP so costs cannot be distinguished, 2) these costs are average costs per child in a year i.e. total cost of all children / number of children so don’t factor in exact duration of status
	CPP	£10,776	Source: DfE Aldaba Document, note: 1) this dataset combines CiN and CPP so costs cannot be distinguished, 2) these costs are average costs per child in a year i.e. total cost of all children / number of children so don’t factor in exact duration of status
	LAC	£44,647	Source: DfE Aldaba Document, note: these costs are average costs per child in a year i.e. total cost of all children / number of children so don’t factor in exact duration of status

	Average full years spent as (rounded upwards):
	EH	1	Estimated typically 3 - 6 months. Note that Early Help case information is not often captured in councils at this aggregate level due to e.g. complexity of Early Help services, differences in definition and lack of statutory data reporting
	CiN	1	Source: Calculation derived from Characteristics_of_children_in_need_2017-18 by DfE, note: as costs figures above are based on average cost per child over the course of a year, we round to show how many full years a child on average spends at each status
	CPP	1	Source: Calculation derived from Characteristics_of_children_in_need_2017-18 by DfE, note: as costs figures above are based on average cost per child over the course of a year, we round to show how many full years a child on average spends at each status
	LAC	2	Source: Calculation derived from Characteristics_of_children_in_need_2017-18 by DfE, note: as costs figures above are based on average cost per child over the course of a year, we round to show how many full years a child on average spends at each status

3	COST OF LONG-TERM OUTCOMES - CARE LEAVERS

	DESCRIPTION
	Argument: Here we estimate the additional cost that Care Leavers (CL - i.e. individuals who have been in care and left care at age 18 i.e. were not adopted, taken under special guardianship order, returned to their family etc. - this is a subset of the LAC population so our calculations are an underestimate of the total cost) cost to government due to some of their worse life outcomes
	Cost calculation: Additional cost due to negative outcome = cost of outcome * (proportion of CL with negative outcome - proportion of non-CL with negative outcome) * CL population

	ASSUMPTIONS

	Estimating the total number of care leavers in the country

	Method: model the number of care leavers per year back over time based on UK population		Source/Comments

	Estimated number of Care Leavers	395,779

	Average lifespan after age 18	58	# of cohorts of care leavers in the country
	# of people leaving care in 2018	9,000	National Statistics- Children looked after in England, 2018
	# of Care Leavers 2007	7,500	Estimate uses pre-2007 numbers to take into account the uptake in LAC numbers following the Baby P incident
	UK population 2007	61,000,000	ONS
	UK population 1947	50,000,000	ONS
	Increase in care population since 2007	120%	There has been a large increase in the number of children in care since 2007, particularly following the death of Baby Peter. Here we take figures back to 2007 so we don't overestimate the number of people who have been in care
	Hypothetical Care Leavercohort 1947	6,148	Assuming that the proportion of care leavers in the population remains constant over time
	Estimated average number of care leavers per year (past 60 years)	6,824

	Criminal Justice - Prison

			Source/Comment
	UK population 2019	65,000,000	ONS
	Unit cost of prison for a year	£34,840	New Economics Foundation
	Total number of prisoners UK	83,000	MoJ
	% of Prisoners that are Care Leavers	26.7%	HMI Prisons
	Number of Prisoners that are Care Leavers	22,133
	% of Care Leavers in prison at any point	5.6%
	% of general population in prison	0.13%
	Additional costs due to Care Leavers	£753,517,931

	Welfare Benefits

			Source/Comment
	Unit cost per year	£3,120	Job-Seekers Allowance and low income benefits (GOV.UK, March 2014)
	UK unemployment rate	4%	ONS, 2019
	% of Care Leavers (aged 19-21) who are NEET	40%	Support for Care Leavers, House of Commons Briefing Paper, 2019: 40% ofCare Leaver(age 19-21) are NEET vs. 15% of all people age 19-21
	% of all people age 19-21 who are NEET	15%	Support for Care Leavers, House of Commons Briefing Paper, 2019: 40% ofCare Leaver(age 19-21) are NEET vs. 15% of all people age 19-21
	Care Leavers unemployment rate	11%	Assuming that Care Leavers are 2.67 times more likely to be unemployed based on LAC being 2.67 times more likely to be NEET
	Additional cost due to Care Leaver	£82,321,967

	Foregone Tax

			Source/Comment
	Average UK salary	£27,600.00	YouGov, 2017; average UK salary is £27,600 according to ONS
	Personal allowance	£11,850.00	gov.uk
	Lower rate income tax	20.0%	gov.uk
	Tax on an average UK salary	£3,150

	UK employment rate	75.0%	ONS, 2019
	Population out of labour force	21%	ONS, 2019
	Care Leavers employment rate	68%	Conservatively assuming that the out-of-labour-force rate is the same for care leavers
	Additional cost due to Care Leaver	£83,113,525

## Cost Assumptions
KEY COST ASSUMPTIONS					KEY OUTPUTS
				For Benefits Case report
Staff Cost Assumptions	Input	note					Cost per local authority adopting family context inc. setup and steady-state
Day rate for IG rep	£186	Source: Stockport & Leeds
Day rate for technical team rep (e.g. developers / User Researchers, etc)	£250	Source: Stockport & Leeds					Number of LAs in Beta Phase 2	4
Day rate for project/ product manager	£236	Source: Stockport & Leeds
Day rate for project sponsor	£268	Source: Stockport & Leeds					Beta Cost
Day rate for a social worker	£164	Source: Stockport & Leeds					Family Context Setup Costs (beta assumes higher cost because FC implemented for the first time)	£989,224.27
Local Authority User Research / BA Support	£186	Source: Stockport & Leeds					Ongoing Product Development and Maintenance Costs (annual, per council)	£222,589.47
Cost of a training day	£500	Not validated					Beta - Collaboration (e.g. coordination, IG and Ethics support, UI/UX, etc)	£300,000
Digital Agency - Developer	£900	Source: Digital Outcomes Specialist Framework					Sub-total	£1,511,814
Digital Agency - Blended day rate for consultant	£900	Source: Digital Outcomes Specialist Framework
Digital Agency - User Research / BA Support	£900	Source: Digital Outcomes Specialist Framework					One-off Costs
				Family Context Setup Costs	£86,011
Infrastructure Costs					Family Matching Algorithm - Implementation	£20,000
Infrastructure / Hosting (per month)	£200	Source: AWS estimation to be validated in Beta					Integrating Additional Datasets in family context	£46,489
				Sub-total	£152,500
Efficiency Gains
Efficiency Factor gained through collaboration (e.g. percentage of full cost)	50%	Source: test assumption in beta					On-going
				Product Development and Maintenance Costs (Beyond MVP)	£33,113
				On-going Family Matching Algorithm Cost	£2,000
				Cost of Collaboration	£4,507
				Sub-total	£39,620

FAMILY CONTEXT PRODUCT SETUP AND ON-GOING COSTS

Family Context Setup Costs (one-off, per council)			Cost per LA w/o collaboration (beta assumes higher cost because FC implemented for the first time)				Cost per LA w/collaboration (roll-out post beta)
			Volume - Days	Rate	Cost in 1 LA		Volume - Days	Rate	Cost in 1 LA
Product development costs					notes
IG rep days			30	£186	£5,591		15	£186	£2,795	based on experience in Alpha
Technical rep days			120	£250	£30,000		60	£250	£15,000	based on experience in Alpha
Project management team days			120	£236	£28,364		60	£236	£14,182	based on experience in Alpha
User research / BA support / UAT (e.g. Social Worker Input / Members of the Digital Team)			120	£186	£22,364		60	£186	£11,182
Digital Agency - Product Development Support (Product Management Days, Developers, User Research / BA Support)			120	£900	£108,000					assume no digital agency needed for local authorities post-beta

Product delivery set up costs - infrastructure, training, launch costs
Trainer days needed			20	£500	£10,000		10	£500	£5,000	Depends on number of area SWs in each LA
Social Worker training on how to use family context			200	£164	£32,717		200	£164	£32,717	no efficiency gain on training
Social Worker time for user research as part of piloting the beta (10 week pilot)			30	£164	£4,908		15	£164	£2,454
Project sponsor days			20	£268	£5,364		10	£268	£2,682	project sponsor time to ensure buy-in

Total Cost per LA					£247,306				£86,011

Ongoing Product Development and Maintenance Costs (annual, per council)			Cost per LA w/o collaboration				Cost per LA w/collaboration
			Volume - Days	Rate	Cost in 1 LA		Volume	Rate	Cost

On-going product management / project management			35	£236	£8,273		18	£236	£4,136
On-going development / data quality control			85	£250	£21,250		43	£250	£10,625
User research / BA support			35	£186	£6,523		18	£186	£3,261
Infrastructure / hosting (per month)			12	£200	£2,400		12	£200	£2,400	no efficiency gain on infrastructure / hosting
Maintaining access to data sources			15	£268	£4,023		8	£268	£2,011
Social worker days			50	£164	£8,179		50	£164	£8,179	no efficiency gain on social worker training
Training Costs			10	£500	£5,000		5	£500	£2,500

Total Cost per LA					£55,647				£33,113

FAMILY CONTEXT FEATURE COSTS - SETUP AND ON-GOING

Family Matching Algorithm - Development (one-off, combined cost)			Total Cost	notes
Discovery			£30,000	update costings once user need more clearly defined
Alpha			£80,000	cost dependent on discovery findings
Beta			£120,000	cost dependent on alpha findings

Total Cost			£230,000

Family Matching Algorithm - Implementation / On-going (ongoing and one-off, per council)			Cost per LA
Cost per local authority implementation			£20,000	cost dependent on beta findings
On-going Family Matching Algorithm Cost			£2,000	cost dependent on beta findings

Cost			£22,000

INTEGRATING ADDITIONAL DATASETS INTO FAMILY CONTEXT - note: these will vary and need to be scoped in beta for each type of provider and data source

Access to data source from within the local authority / local partners (one-off, per data source, per council)			Cost per LA w/o collaboration				Cost per LA w/collaboration

Local Authority Controlled Data Source			Volume - Days	Rate	Cost		Volume	Rate	Cost
IG Rep			5	£186	£932		3	£186	£466
Project Sponsor Input			5	£268	£1,341		3	£268	£670
External Support on IG. Ethics, Etc			3	£900	£2,250		1	£900	£1,125

Cost					£4,523				£2,261

Local Partner Data Source (e.g. Police, NHS, etc)			Volume - Days	Rate	Cost		Volume	Rate	Cost
IG Rep			10	£186	£1,864		5	£186	£932
Project Sponsor Input			5	£268	£1,341		3	£268	£670
External Support on IG. Ethics, Etc			5	£900	£4,500		3	£900	£2,250

Cost					£7,705				£3,852

Access to data source from partner local authorities / national bodies (one-off, per data source, per council)

Local Authority Controlled Data Source From Another Local Authority			Volume - Days	Rate	Cost		Volume	Rate	Cost
IG Rep			15	£186	£2,795		8	£186	£1,398
Project Sponsor Input			5	£268	£1,341		3	£268	£670
External Support on IG. Ethics, Etc			5	£900	£4,500		3	£900	£2,250

Cost					£8,636				£4,318

External Data Source with National Coverage (e.g. National NHS, etc)			Volume - Days	Rate	Cost		Volume	Rate	Cost
IG Rep			20	£186	£3,727		10	£186	£1,864
Project Sponsor Input			5	£268	£1,341		3	£268	£670
External Support on IG. Ethics, Etc			10	£900	£9,000		5	£900	£4,500

Cost					£14,068				£7,034

COST OF COLLABORATION

Cost of Collaboration as a percentage of total cost			20%	needs to be tested in beta

Cost Per Local Authority			Per Local Authority		Cost Per Local Authority
Project Setup Costs			1		£32,259		note: collaboration is based on subtracting the costs of family context w/o collaboration from the cost with collaboration multiplied by the expected cost of supporting collaboration between LAs on family context
Product Development and Maintenance			1		£4,507		note: collaboration is based on subtracting the costs of family context w/o collaboration from the cost with collaboration multiplied by the expected cost of supporting collaboration between LAs on family context
Beta - Collaboration (e.g. coordination, IG and Ethics support, UI/UX, etc)			1		£300,000		note: to cover collaboration and coordination

Total Cost per LA					£336,766

## Financial Model - detailed work
Phase				Discovery / Alpha	Beta		Live Product					Notes		Checks
Beta Switch				0	1	2	2	2	2	2	2	2
Year					2019 / 2020	2020 / 2021	2021 / 2022	2022 / 2023	2023 / 2024	2024 / 2025	2025 / 2026	2026 / 2027

KEY ASSUMPTIONS

Benefits Off-Set				1	year (offset up to 3 years)

Savings from social workers not having to spend time chasing information
Cost Saving per council on assessments				£112,895	total benefits w/ 60% confidence factor applied
additional % of total benefit realised each year				12.50%	The full benefits will not be achieved with early versions of the tool. The % of the total benefits that are achieved is assumed to increase year on year

Savings from children and families not escalating unnecessarily
Cost saving per council of children and families not escalating unnecessarily				£209,025	total benefits w/ 60% confidence factor applied
additional % of total benefit realised each year				12.50%	The full benefits will not be achieved with early versions of the tool. The % of the total benefits that are achieved is assumed to increase year on year

Local Authorities
Number of Local Authorities - On-Boarded				0	4	4	4	4	6	6	6	6
Number of Local Authorities - Cumulative				0	4	8	12	16	22	28	34	40

Additional Features
Family Context Algorithim - Discovery				0	0	0	1	0	0	0	0	0
Family Context Algorithim - Alpha				0	0	0	1	0	0	0	0	0
Family Context Algorithim - Beta				0	0	0	0	1	0	0	0	0
Family Context Algorithim - Live				0	0	0	0	0	1	1	1	1

Data Sources (year added to the MVP on a cumulative basis)
LA-controlled data sources - local-only data				0	0	2	2	2	2	2	2	2
LA-controlled data sources - data shared across LA partners				0	0	0	2	5	5	5	5	5
Externally-controled data sources - local-only data				0	0	2	2	2	2	2	2	2
Externally-controled data sources - multi-region/ national				0	0	0	0	0	0	2	2	2
TOTAL NUMBER OF DATA SOURCES				0	0	4	6	9	9	11	11	11

BENEFITS BREAKDOWN

Benefit ramp-up year on year
Savings from social workers not having to spend time chasing information				0.0%	12.5%	25.0%	37.5%	50.0%	62.5%	75.0%	87.5%	100.0%	The full benefits will not be achieved with early versions of the tool. The % of the total benefits that are achieved is assumed to increase year on year
Savings from children and families not escalating unnecessarily				0.0%	12.5%	25.0%	37.5%	50.0%	62.5%	75.0%	87.5%	100.0%	The full benefits will not be achieved with early versions of the tool. The % of the total benefits that are achieved is assumed to increase year on year

Benefits Per Year
Savings from social workers not having to spend time chasing information				£0	£0	£56,448	£225,790	£508,028	£903,161	£1,552,308	£2,370,798	£3,358,630	conservative assumption - benefits do not begin until the following year
Savings from children and families not escalating unnecessarily				£0	£0	£104,512	£418,049	£940,611	£1,672,197	£2,874,089	£4,389,518	£6,218,483	conservative assumption - benefits do not begin until the following year

TOTAL BENEFITS PER ANNUM				£0	£0	£160,960	£643,840	£1,448,639	£2,575,358	£4,426,397	£6,760,316	£9,577,114

COST BREAKDOWN

Product Development Costs
Discovery				£100,000
Alpha				£170,000

Sub-total				£270,000	£0	£0	£0	£0	£0	£0	£0	£0			0

Local Authority Costs - Product Roll-Out and Maintaince Costs
Setup Costs - Rolling Out MVP				£0	£989,224	£344,046	£344,046	£344,046	£516,068	£516,068	£516,068	£516,068			0
On-going - Product Development and Maintanence Costs (Beyond MVP)				£0	£222,589	£264,906	£397,359	£529,812	£728,492	£927,172	£1,125,851	£1,324,531			0

Sub-total				£0	£1,211,814	£608,952	£741,405	£873,858	£1,244,560	£1,443,240	£1,641,920	£1,840,599

Local Authority Costs - Additional Features
Family Matching Algorithim
Discovery				£0	£0	£0	£30,000	£0	£0	£0	£0	£0			0
Alpha				£0	£0	£0	£80,000	£0	£0	£0	£0	£0			0
Beta				£0	£0	£0	£0	£120,000	£0	£0	£0	£0			0
Cost per local authority implementation				£0	£0	£0	£0	£0	£440,000	£120,000	£120,000	£120,000			0
On-going Family Matching Algorithm Cost				£0	£0	£0	£0	£0	£44,000	£56,000	£68,000	£80,000			0

Sub-total				£0	£0	£0	£110,000	£120,000	£484,000	£176,000	£188,000	£200,000

Local Authority Costs - Data Sources Cost
Local Authority Controlled Data Source				£0	£0	£36,182	£18,091	£18,091	£27,136	£27,136	£27,136	£27,136
Local Partner Data Source (e.g. Police, NHS, etc)				£0	£0	£0	£92,455	£77,045	£115,568	£115,568	£115,568	£115,568
Local Authority Controlled Data Source From Another Local Authority				£0	£0	£69,091	£34,545	£34,545	£51,818	£51,818	£51,818	£51,818
External Data Source with National Coverage (e.g. National NHS, etc)				£0	£0	£0	£0	£0	£0	£393,909	£84,409	£84,409

Sub-total				£0	£0	£105,273	£145,091	£129,682	£194,523	£588,432	£278,932	£278,932

Collaboration Costs
Beta - Collaboration				£0	£300,000	£0	£0	£0	£0	£0	£0	£0
Project Setup Costs				£0	£0	£129,036	£129,036	£129,036	£193,554	£193,554	£193,554	£193,554
Product Development and Maintenance				£0	£0	£36,055	£54,082	£72,109	£99,150	£126,191	£153,232	£180,273

Sub-total				£0	£300,000	£165,090	£183,118	£201,145	£292,704	£319,745	£346,785	£373,826

TOTAL COST PER ANNUM				£270,000	£1,511,814	£879,315	£1,179,613	£1,324,685	£2,215,787	£2,527,416	£2,455,637	£2,693,358

NET BENEFIT FROM FAMILY CONTEXT				(270,000)	(1,511,814)	(718,355)	(535,774)	123,954	359,571	1,898,981	4,304,679	6,883,756

NPV				£7,422,332