ALPHA RECOMMENDATIONS AND NEXT STEPS

---
ALPHA RECOMMENDATIONS
ALPHA RECOMMENDATIONS
COLLECT NEXT OF KIN TELEPHONE NUMBER
Registration Services start to collect informant (e.g. ‘Next of Kin’) telephone number, and the in-built RON is updated to include it
PUBLISH AND PUBLICISE THIS OPPORTUNITY
In the interim, the ‘how-to’ guides created during this alpha are published online and publicised to increase access to registrations data amongst housing services
1
2

---
RECOMMENDATION 1 – COLLECT NEXT OF KIN CONTACT TELEPHONE NUMBER
RECOMMENDATION 1 – COLLECT NEXT OF KIN CONTACT TELEPHONE NUMBER
RECOMMENDATION
Collect next of kin telephone number
Registration Services start to collect informant (e.g. ‘Next of Kin’) telephone number, and the in-built RON is updated to include it
IMPLEMENTATION PLAN
Phase 1 – update RON report
GRO / Home Office amends the RON back-end to:
include informant telephone number (e.g. Next of Kin) within the existing Health report
remove unnecessary data fields from the report, such as ‘Place of Birth’ and ‘Occupation’.
reorder data fields to include the most relevant data at the beginning of the spreadsheet
Phase 2 – registration practice change
GRO works with local registrations services so that informant telephone number (e.g. Next of Kin) is also captured within RON as standard when registering a death
PARTNERS
General Register Office – decide to update Registration Service protocols to include informant (e.g. ‘Next of Kin’) telephone number, and update RON system
Registration Services – registration staff begin capturing informant (e.g. ‘Next of Kin’) telephone number in RON system as part of the standard process to register a death

---
RECOMMENDATION 2 – PUBLISH AND PUBLICISE THIS OPPORTUNITY
RECOMMENDATION 2 – PUBLISH AND PUBLICISE THIS OPPORTUNITY
RECOMMENDATION
Publish and publicise this opportunity
In the interim, publish and publicise the ‘How-to’ guides to increase access to registrations data amongst housing services
IMPLEMENTATION PLAN
Phase 1 – post to websites
We have created two guides to help housing services access the currently available in-built RON report (see Appendix 1). This includes an end-to-end process guide (‘How-to’ guide), and a template data sharing application
MHCLG, DCMS, and the GRO to publish the guides online where they will be accessible to housing services (e.g. GRO or MHCLG website)
Phase 2 – contact housing services
MHCLG should contact all housing services to inform them of the opportunity. The DCMS has agreed to release a report and blog which will include a case studies on this use case, plus links to the ‘How-to’ guides
PARTNERS
General Register Office – post the template data sharing application produced during alpha on website
DCMS, Digital Economy Unit – publish the ‘How-to’ guide and a case study online
MHCLG, Local Digital Team – contact housing teams to publicise the opportunity

---
KEY CONSIDERATION FOR RECOMMENDATIONS: GENERAL REGISTER OFFICER RESOURCE REQUIREMENT
If more local housing services decide to request data direct from their local Registration Service (e.g. as a result of the alpha and MHCLG and others publishing the potential impact), many of these applications will need to be reviewed by the GRO for approval (i.e. applications that involve more than 1,000 records a year must be reviewed by the GRO rather the relevant local Registration Service).
GRO itself will derive no benefit from sharing this information. Its mandate is to share data with central government. As a result, MHCLG may want to consider funding the GRO to make the required changes to their in-built RON report and registration data collection process. The benefits case above suggests that the savings to local authorities and benefits to families make it worthwhile.

---
COMPARISON OF THE LIKELY BENEFITS OF THE RECOMMENDED MVP VERSUS THE CURRENTLY AVAILABLE IN-BUILT RON REPORT
Benefit	Benefits comparison of MVP with in-built RON report (i.e. informant address rather than tel)?
Financial benefits
Reduced Housing Officer time spent difficult cases	MVP would result in a slightly higher amount of time saved on difficult cases in comparison to the in-built RON report.
Reduction in rent arrears from void properties	MVP would result in a slightly larger reduction in rent arrears in comparison to the in-built RON report.
Reduction in TA spending from void properties	MVP would result in a slightly larger reduction in TA spending in comparison to the in-built RON report.
Social and wider unquantified benefits
Money saved from removing local TUO contract	No difference between MVP and in-built RON report
Reduced time of other public services (e.g. public trustee)	MVP would result in a slightly larger reduction in time saved of other public services
Support for tenants who lived with deceased tenant	No difference between MVP and in-built RON report
Internal culture change	No difference between MVP and in-built RON report
Residents do not have to purchase death certificates and bring them into the housing service	No difference between MVP and in-built RON report

---
PROPOSED ROADMAP AND PHASING FOR RECOMMENDATIONS 1 AND 2
PROPOSED ROADMAP AND PHASING FOR RECOMMENDATIONS 1 AND 2
Rec 1
MHCLG / GRO publish ‘How-to’ guides and publicise the opportunity
Potential to publicise alpha findings more widely so other local public services can begin to take advantage
Rec 2
Alpha
GRO update current RON report to include tel and remove fields
GRO work with local Registration Services to collect ‘Next of Kin’ tel as standard
Capturing tel becomes part of business as usual