## Meta_input
Project:	Back-office Planning System

Lead Council:	Southwark

Contibutors:	Martyn Evans (Unboxed), Jack Ricketts (Southwark)

Date Completed:	23/12/2019

## BoPS_Net_Present_Value
BoPS software costs
Cost of MVP	£543,698	See "BoPS software costs" for assumptions
Cost of full service	£868,412
Ongoing development (annual)	£542,194
Support & maintenance	£36,000

Council costs			See "Council costs" for assumptions
	Current systems	With BoPS
Annual licence fees	£34,250	£10,000
Cost of transactions	£568,954	£367,222	No savings expected during first 2 years of development as BoPS MVP may have to run in parallel to existing systems
Benefit from transactions	£0	£0
Renewal/implementation cost	£250,000	£50,000
Years between renewals	10	0	Assume new councils adopt BoPS at renewal time so save difference between renewal and implementation

	MVP (Minors)	Full system (all applications)
	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30
Councils onboard (total)	3	5	10	20	30	40	50	60	70	80	90		365 planning authorities in England. Assume 25% on-boarded within 10 years

Software costs
Design and development (outsourced)	£543,698	£868,412
Ongoing enhancement (outsourced)	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194	£542,194
Support and maintenance (outsourced)	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000	£36,000
Product management (cross-council team)	£60,000	£100,000	£100,000	£130,000	£130,000	£130,000	£130,000	£150,000	£150,000	£150,000	£150,000
Total costs	£1,181,892	£1,546,606	£678,194	£708,194	£708,194	£708,194	£708,194	£728,194	£728,194	£728,194	£728,194

Annual savings (per council)
Transaction savings	£0	£0	£201,732	£201,732	£201,732	£201,732	£201,732	£201,732	£201,732	£201,732	£201,732
License savings	£0	£0	£24,250	£24,250	£24,250	£24,250	£24,250	£24,250	£24,250	£24,250	£24,250
Other benefits	£0	£0	£0	£0	£0	£0	£0	£0	£0	£0	£0
Implementation/renewal (new councils only)	£0	£0	£200,000	£200,000	£200,000	£200,000	£200,000	£200,000	£200,000	£200,000	£200,000
Total savings	£0	£0	£3,259,822	£6,519,644	£8,779,466	£11,039,287	£13,299,109	£15,558,931	£17,818,753	£20,078,575	£22,338,397

Annual income
License fees (per council)	£0	£0	£10,000	£10,000	£10,000	£10,000	£10,000	£10,000	£10,000	£10,000	£10,000
Total income	£0	£0	£100,000	£200,000	£300,000	£400,000	£500,000	£600,000	£700,000	£800,000	£900,000

Total net benefits per year	-£1,181,892	-£1,546,606	£2,681,628	£6,011,450	£8,371,272	£10,731,094	£13,090,916	£15,430,738	£17,790,559	£20,150,381	£22,510,203
Discount factor	100%	97%	93%	90%	87%	84%	81%	79%	76%	73%	71%
Discounted net benefits	-£1,181,892	-£1,494,305	£2,503,329	£5,421,984	£7,295,080	£9,035,293	£10,649,468	£12,128,420	£13,510,356	£14,784,959	£15,957,906

Net Present Value	£88,610,598

## Detailed_working
Supporting information
Please provide supplementary info and calculations for your inputs.

	1. Could you include an assumptions register? This should list the assumptions made, what estimates are produced and why, what are the sources of information used. As a minimum, provide answers to :	see "BoPS software costs"
	What are the sources for the cost figures, and can we see them?	see "Application types and time"
	If you've derived any figures yourselves, how have you done so? Can we see their working out?	see "Application types and time"
	2. Can you provide some sensitivity analysis?
	Can they explain how confident you are about achieving these figures?
	How possible is it that the costs will spiral beyond the figures stated here?
	What about risks - e.g. what if councils are reluctant to sign up?	There are over 300 planning authorities currently all using one of 3/4 largely disliked systems. To get 90 councils using BoPS over 10 years seems reasonable. Break even seems to be between 5-10 councils in year 3
	A high, medium, and low risk scenario would be good to see, with you justifying which scenario you consider most likely.	The model is quite complex with lots of potential variables. We can adjust the figures and see the impact on the Net Pesent Value but it would be difficult to identify those scenarios
	2. Please provide information in the 'detailed workings' tab, as it is currently empty (including points 1 and 2). This especially relates to the 'cost of transaction' information in rows 10-13. Please include information on how the numbers were worked out and your definition of a transaction. We are unable to verify the provided numbers until this information is given.	see "Council costs" and "Application types and time"
	3. We need information on how you calculated the scaling. What information is it based on?	If by scaling you mean onboarding councils please see above
	4. How confident are you in your Support and maintenance (outsourced) costs staying the same even when you have 100 councils on board?	Front-line/customer support would be provided by the Product Team which does scale in the model. The software support and hosting costs may increase slightly but not significantly as this is not a "high transaction" services and unlikely to "spike"
	5. For your spreadsheet it is not clear about how the annual costs of the new BoPS software interact with the costs of the previous system. You estimate that the new software will save approximately a third of the costs of the previous system (Cells B10 & C10) - but how does this interact with the additional cost of ~£660 a year for the new system? And how will these costs change as further councils sign up to use the system?	Transaction savings are per council. Software costs are mostly across the whole system. Investment in ongoing system improvements are largely independent on the number of customers with a SAAS model. We anticipate ongoing central government funding to maintain the level of investment required

## BoPS_software_costs_(outsourced
		Digital team profile
Role	Day rate	Discovery (research)	Alpha (prototyping)	Beta (build)	Day rates based on average rates of three suppliers 2020 rates as published on GCloud
Senior Service Designer	£1,117	100%	40%	40%
UX/UI Designer	£850	0%	100%	100%					1117
Content Designer	£850	0%	40%	40%					850
User Researcher	£850	100%	100%	40%					850
Technical Architect	£1,117	50%	50%	50%					850
Senior Developer	£1,000	0%	0%	100%					1117
Developer	£875	0%	100%	100%					1000
Junior Developer	£650	0%	0%	100%					875
Delivery Manager	£942	40%	40%	40%					650
Cost per sprint (2 weeks)		£29,022	£42,970	£54,370					941.7

Phase sprints		Discovery (research)	Alpha (prototyping)	Beta (build)	Cost
MVP		0	0	10	£543,698	Discovery and alpha already completed					549000
Full service		3	3	12	£868,412					869100
Enhancement (annual)		3	3	6	£542,194	Resources spread throughout the year					539700

Working hours support (annual)					£24,000	Based on typical Unboxed contract					24000
AWS hosting (annual)					£12,000	Estimated based on 100 councils maximum. May be lower in early years but higher later					12000

## Council_costs
Council	Planning Software	Transition Cost	Annual Cost	A sample of information gathered from research and historical FOI requests.
Southwark	Idox Acolaid to Idox Uniform *	£500,000	£100,000	In some instances, software covers multiple services.				£34,250	Median now used
Surrey Heath	Idox Acolaid to Idox Uniform *	£264,000		* as of Jan 2020 - upgrade works still on-going
Hounslow	Northgate iLAP, iPlan, and iGaz	?	£31,000	The variation in costs reflects supplier or customer hosting				£34,250	Median now used
Kent	DEF Mastergov	?	£17,140					£34,250	Median now used
Central Bedfordshire	Idox Acolaid	?	£125,000					£34,250	Median now used
Maidstone	Idox Uniform	?	£14,603					£34,250	Median now used
Bexley	Idox Uniform	?	£53,000					£34,250	Median now used
South Tyneside	Northgate M3	?	£37,500					£34,250	Median now used
Taunton Deane	Idox Acolaid	?	£12,850					£34,250	Median now used
Falkirk	Idox Uniform	?	£40,000					£34,250	Median now used
Mendip	Northgate Assure	?	£23,000					£34,250	Median now used
Average			£34,250	Median now used				£34,250	Median now used

BoPS annual license fee			£10,000	Nominal figure, can be adjusted

Number of planning applications per year (England)
	% *	# applications	hrs/application *	Total hours	Cost		*See "Application types and time"
Fast track	44.49%	196,271	7.38	1447680.625	£86,860,838
Full	7.24%	31,936	29.42	939474.5622	£56,368,474
Other	48.27%	212,921	5.04	1073980.699	£64,438,842
Total		441,133			£207,668,153		https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/741789/Planning_Applications_April_to_June_2018_-_statistical_release.pdf
							"Authorities that undertake county level planning activity – which includes counties, unitary authorities, London boroughs, metropolitan districts, national parks and development corporations - received 1,033 ‘county matters’ applications in the year ending September 2019 (Table 4 and Live Table P144). This compares with around 440,100 planning applications received by authorities that undertake district level planning activities."
For cost calculations
Cost per hour	£60		Southwark - simple	£538,672	£269,336		Estimate based on conversations with Southwark planning management
# planning authorities (England)	365	See below					https://en.wikipedia.org/wiki/Local_planning_authority

Potential cost savings per council
		Target saving *	Current cost	Saving	New cost		* Target savings estimated based on observations of complexity and waste
Fast track		50%	£237,975	£118,987	£118,987
Full		25%	£154,434	£38,609	£115,826
Other		25%	£176,545	£44,136	£132,409
Total			£568,954	£201,732	£367,222		NB. Total cost to councils could be as high as £1,394,000 per council according to Connected Places Catapult/Arup, October 2019, Research into the cost of key activities in the planning system
				£73,632,248
Renewal costs				£18,408,062
Existing systems renewal costs					£250,000	Conservative figure based on Southwark upgrade from Accolaid to Uniform (estimated at £500k). Figure validated by Surrey Heath district going through similar "upgrade".
BoPS implementation costs (estimated)					£50,000	SAAS service, no renewal costs but one off implementation, reduced training due to uesr-centred design, no inflated commercial fees

Planning authorities in England
Type of authority	#
London borough councils	32
metropolitan borough councils	36
non-metropolitan district councils	201
non-metropolitan county council	27
unitary authority councils	55
the City of London Corporation	1
the Council of the Isles of Scilly	1
national parks authorities including the Broads Authority	10
mayoral development corporations	2
Total	365

## Application_types_and_time
Application numbers and processing time by type across 5 councils
All fiigures are based on the amount of time council officers spend processing a planning application, from receipt, through validation to publication of a decision
	Southwark				Tower Hamlets				Redbridge				Lambeth				Huntingdonshire
	% total applications	# applications	Hrs/application	Total hours	% total applications	# applications	Hrs/application	Total hours	% total applications	# applications	Hrs/application	Total hours	% total applications	# applications	Hrs/application	Total hours	% total applications	# applications	Hrs/application	Total hours
Fast track	38.40%	1938	4.6	8978	17.94%	444	9.3	4135	48.37%	2280	3.1	7043	57.08%	3158	0.0	0	48.81%	1194	19.3	23043
Certificates of lawfulness	6.80%	343	1.5	515	5.25%	130	1.5	195	18.94%	893	1.5	1339	9.42%	521				0		0
Full - Householder	15.30%	772	3.5	2703	7.67%	190	7	1329	24.28%	1144	3.5	4005	30.87%	1708			32.09%	785	2	1570
Full - Minor (1-9 dwellings)	16.30%	823	7	5760	5.02%	124	21	2610	5.15%	243	7	1699	16.79%	929			16.72%	409	52.5	21473
Full	6.70%	338	14.6	4947	18.40%	456	36.5	16614	7.56%	356	12.8	4546	4.57%	253	0.0	0	2.62%	64	150.0	9600
Full - Major	0.60%	30	60	1817	1.59%	39	200	7874	0.53%	25	60	1499	2.01%	111			2.62%	64	150	9600
Full - Strategic	0.10%	5	200	1010		0		0	0.08%	4	200	754	0.23%	13				0		0
Full - Other minor and change of use	6.00%	303	7	2120	16.81%	416	21	8741	6.95%	328	7	2293	2.33%	129				0		0
Other	54.90%	2771	1.1	3170	63.65%	1576	19.3	30474	45.03%	2122	1.4	2904	38.35%	2122	0.0	0	48.57%	1188	1.7	2075
Approval of details, reserved matters, conditions, variations, etc	33.20%	1676	1	1676	28.87%	715	35	25019	5.68%	268	1	268	14.59%	807				0		0
Condition		0		0		0		0		0		0		0			12.35%	302	0.5	151
Trees	5.90%	298	1	298	5.78%	143	3	429	6.16%	290	1	290	8.13%	450				0		0
All other applications	15.80%	798	1.5	1196	29.00%	718	7	5026	33.19%	1564	1.5	2346	15.06%	833			16.31%	399	2	798
Pre-apps in cons/listed buildings etc		0		0		0		0		0		0	0.58%	32				0		0
Preliminary enquiry/PDE		0		0		0		0		0		0		0			9.81%	240	3	720
Non-material ammendments		0		0		0		0		0		0		0			5.48%	134	0.5	67
Priors		0		0		0		0		0		0		0			4.62%	113	3	339
Totals		5048		17095		2476		51223		4713		14493		5533				2446		34718

Application type breakdown across 5 councils
	Southwark	Tower Hamlets	Redbridge	Lambeth	Huntingdonshire	Total	%		Data sources
Fast track	1938	444	2280	3158	1194	9015	44.49%		Limited activity analysis from Southwark Council
Full	338	456	356	253	64	1467	7.24%		Email correspondence with other councils
Other	2771	1576	2122	2122	1188	9779	48.27%		Local planning registers
Total	5048	2476	4758	5533	2446	20261
			Modified total to make 100%
Processing time (hours) per application type across 4 councils
	Southwark	Tower Hamlets	Redbridge	Huntingdonshire	Total	%	Hrs/application	Excludes Lambeth - no time data
Fast track	8978	4135	7043	23043	43198	36.76%	7.38
Full	4947	16614	4546	9600	35707	30.38%	29.42
Other	3170	30474	2904	2075	38624	32.86%	5.04
Total	17095	51223	14493	34718	117529

Application processing costs per council				Connected Places Catapult/Arup, October 2019, Research into the cost of key activities in the planning system
Householder (extensions, etc)			£304,000
Small Residential (1-50 units)			£771,000
Large Residential (50-200 units, mainly but not exclusively residential)			£181,000
Mixed use scheme (residential with a significant element of other uses)			£138,000
Total			£1,394,000