## Cover
Guidance on Providing Benefits and Business Case Info

	This template provides guidance on the data we would expect to be produced as part of the benefits and business case of your project. This data will be used to support the wider business case of our programme.
	We understand that all projects are at an early stage, and all inputs will be estimates based on best efforts and available data. You are encouraged to provide your best estimate and iterate as you find more data.
	To allow iteration, we recommend you provide MHCLG with an early view of your data, at least 1 month before your estimated project completion.

Instructions
-	Please complete as much of the 'Model Input' sheet as possible, with appropriate notes for sources and calculation methodology.
-	Expectations for projects in Discovery phase are significantly reduced - please complete the sections relevant to your project phase.
-	Important inputs are highlighted in red, so focus on these.
-	Please make use of notes and add supplementary info to explain your calculations and sources in the 'Detailed working' tab.
-	Please focus on benefits and costs to public sector organisations, particularly to local authorities. Where you include costs and benefits to citizens, private sector etc, please show this in the breakdown.
-	You can use these inputs to create your economic appraisal as part of your business case, as in the 'Example appraisal' sheet.
-	Inputs are requested for participating councils as well as an estimate for the 'average UK council' that might deploy this service. In many cases, you may need to assume similar parameters between these categories.
-	Please send any supporting documentation.

Tips for completing this template
-	Given the lack of data on projects that are still in development, please make assumptions based on suitable evidence - similar systems, historical examples and expert advice.
-	Use the GDS Benefits Handbook for reference assumptions, e.g. on staff costs and transactions costs. These should be adjusted for your circumstances where necessary.
-	Where a new service will reduce an existing cost base (e.g. digitising an analog service, reducing manual entry), make a conservative assumption on what % of costs could be avoided using a reference point.
-	Make use of examples of benefits that have already been achieved in similar areas.

## Meta_input
Project:	Discovery into processing Revenues and Benefits data and creating a user-centred, cost-effective system.

Lead Council:	Teighnbridge

Contibutors:	Snook, Strata, Teignbridge, Basildon & Brentwood

Date Completed:	14th April 2020

Initial estimate costs have been developed based on data from half the partners but they require further input from the partnership before they can be shared more widely. / - Information on volumes is based on data provided by Basildon, Brentwood & Teignbridge between the period 1st April 2018 and 31st March 2019 aggregated with estimates for Sedgemoor, Exeter and East Devon which are derived from the relative number of residential dwellings. / - Revenues and Benefits costs have been estimated based on the costs of the Strata Service Solutions and scaled to reflect 5 local authorities (Basildon and Brentwood is a joint service).Costs are based on 2018/19 actuals from Strata Service Solutions, with estimates applied to the proportion of their services that are associated with the Revenues and Benefits services. An inflationary uplift of 2% for staff and 2.5% for supplies and services has been applied. It is recognised that local authorities have different suppliers and IT support service models. / - Productivity opportunities are based on estimates from Basildon, Brentwood & Teignbridge / - The running costs of an open source system have been estimated and compared to the current cost. These costs are indicative and dependent on the governance model put in place and business model.

## Model_input
Benefits Capture Template				For Completion
Please complete in £ or % figures as appropriate. See Cover page for instructions			Example category breakdown / Change/add rows as necessary	For lead council	For partner councils (average)	For typical UK council	For UK (scaled)	Notes
Opportunity sizing - all phases

Annual cost of the problem / Benefit potential
		Revs and Bens IT system running cost saving	Estimated average cost of running the current R&B IT system (staff, infrastructure & licences) £265k v est. cost of running open source system £163k / The est. cost of running an open source system is significantly dependent on the governance model put in place and business model and therefore this figure could be significantly under estimated	£100,000	£100,000	£100,000	£8,500,000	Figures rounded to nearest £10k / UK figure estimate = £100k saving X 85 councils (25% taking up the system. See note below regarding estimated take up level)
		Productivity opportunity	It is estimated that a new system could deliver productivity efficiencies of 6-15%. This has been applied to the number of staff and the average cost of an FTE to provide a figure on efficiency. / LOW estimate £76k / HIGH estimate £190k / Mid point used for this table cost per council / Estimated salary is £40k including oncosts. No. of fewer FTEs required per council required estimated to be 1.9 - 4.8. This is based on an estimated 190 staff across 6 partners, excludes staff in council contact centres dealing with revs and bens enquiries	£130,000	£130,000	£130,000	£11,050,000	Figures rounded to nearest £10k / UK figure estimate = £100k saving X 85 councils (25% taking up the system. See note below regarding estimated take up level)

		Total		£230,000		£230,000	£19,550,000

Number of relevant councils
		Number of councils that have confirmed there is benefits potential (e.g. through survey)	61 survey respondents, 74% expressed interest	NA	NA	NA	45
		Theoretical number of councils that could realise benefits potential	Have estimated 25%-60% of the estimated 340 councils who have a system supplied by one of the three suppliers in the market	NA	NA	NA	85-204	We assume a biased in the survey responses in the basis those who replied to the survey are engaged and therefore more likely to respond positively to questions around if they are interested in taking up a new system. As such estimated national take up is challenging to predict so a range of 25-60% has been assumed.

Option ROI modelling - Alpha and Beta only

Variable net benefits
	Annual variable benefits
		Benefits from providing the service which increase with digital uptake.	e.g. Channel shift
			e.g. Demand reduction
			e.g. Process efficiency
		Total

	Annual variable costs
		Change in running costs that vary depending on digital uptake.	e.g. cost of any cloud services
			e.g. customer support staff cost
		Total

	Projected growth rate in demand
		What do you expect to happen to demand for this service?	Digital uptake
			Demand driver, e.g. adult social care
		Total

Fixed net benefits
	Annual fixed benefits
		Benefits that arise from delivering the service, regardless of uptake by users	e.g. reduced software licence fees
		Total

	Annual fixed costs
		Change in annual overheads that arise from delivering the service, regardless of uptake by users	e.g. Staff Cost
			e.g. Capital and Equipment
			e.g. Training
			e.g. Marketing
		Total

Development and delivery costs
	Development and delivery cost
		Expected cost of developing project through to live service	e.g. build and deliver Alpha
			e.g. build and deliver Beta
			e.g. deliver Live
		Total

	Effect of collaboration on costs for future deployments (%, +ve for higher, -ve for lower)
		How much higher is development cost for the lead council compared to a noncollaborative project?		Should be positive
		How much lower will it be for the average council that reuses project outputs? E.g. lower development time				Should be negative
		Total

Renewal costs
	Refresh/renewal costs
		What semi-regular costs will be expected for renewing the service?	e.g. contract renewal
		E.g. cost of renewing contract, cost of further development time for refresh.	e.g. development time
		Total

	Effect of project on renewal cost
		What is effect of the project on cost of renewal?	e.g. lower procurement cost

		Total

	Number of years between renewals (E.g. contract length)

Number of councils
	Number of councils in UK that are willing and able to adopt this service
		Number of councils where this service could apply (i.e. they operate similar systems)		NA		NA
		Number of councils that have indicated interest in this project		NA		NA
		Number of councils to adopt per year		NA		NA

## Example_appraisal
Example Cost Benefit Analysis

	The example below, with dummy numbers, compares costs and benefits for a proposed option to a default Do Nothing option.
	Note that this calculation does not include adjustments for confidence, sensitivity analysis etc.

Example data
	Suppose your project is to build a new transactional online service.
	Your current system costs and benefits are typical of a UK council, and are as follows:
		Annual licence fees	£10,000
		Cost of transactions	£10,000
		Benefit from transactions	£50,000
		Renewal cost	£5,000
		Years between renewals	10

	Developing a new service will cost the lead council:		£1,000,000

	For all councils
		Implementation costs	£20,000
		Annual licence fees	£5,000
		Cost of transactions	£10,000
		Benefit from transactions	£100,000
		Renewal cost	£2,000
		Years between renewals	10

	Number of councils assumed to adopt per year		20
	Number of years of adoption		5

	To analyse this data we need to make a decision on how to treat the baseline. We can either (1) incorporate the current system into the baseline and calculate benefits against this, or (2) we can separately calculate benefits for each option and compare them at the end.

1) Compare preferred option to Do Nothing option
	Set out the preferred option flow of benefits and the Do Nothing flow of benefits as separate scenarios

			Preferred option					Do Nothing option
			Total	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30		Total	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30
	Costs and benefits:
		Cost of lead development		-£1,000,000					£0
	Per council:
		Cost of implementation		-£20,000					£0
		Licence fees		-£10,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000	-£5,000			-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000
		Cost of transactions		-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000			-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000	-£10,000
		Benefit of transactions		£50,000	£100,000	£100,000	£100,000	£100,000	£100,000	£100,000	£100,000	£100,000	£100,000	£100,000			£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000
		Cost of renewal					-£2,000					-£5,000
				£10,000	£85,000	£85,000	£85,000	£85,000	£83,000	£85,000	£85,000	£85,000	£85,000	£85,000			£30,000	£30,000	£30,000	£30,000	£30,000	£25,000	£30,000	£30,000	£30,000	£30,000	£30,000

	Councils adopting			20	20	20	20	20	0	0	0	0	0	0			20	20	20	20	20	0	0	0	0	0	0

	Cohort size	Y1		20	20	20	20	20	20	20	20	20	20	20			20	20	20	20	20	20	20	20	20	20	20
		Y2			20	20	20	20	20	20	20	20	20	20				20	20	20	20	20	20	20	20	20	20
		Y3				20	20	20	20	20	20	20	20	20					20	20	20	20	20	20	20	20	20
		Y4					20	20	20	20	20	20	20	20					20	20	20	20	20	20	20	20
		Y5					20	20	20	20	20	20	20					20	20	20	20	20	20	20
	Cohort net benefit
		Y1		£200,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,660,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000			£600,000	£600,000	£600,000	£600,000	£600,000	£500,000	£600,000	£600,000	£600,000	£600,000	£600,000
		Y2			£200,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,660,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000				£600,000	£600,000	£600,000	£600,000	£600,000	£500,000	£600,000	£600,000	£600,000	£600,000
		Y3				£200,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,660,000	£1,700,000	£1,700,000	£1,700,000					£600,000	£600,000	£600,000	£600,000	£600,000	£500,000	£600,000	£600,000	£600,000
		Y4					£200,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,660,000	£1,700,000	£1,700,000					£600,000	£600,000	£600,000	£600,000	£600,000	£500,000	£600,000	£600,000
		Y5					£200,000	£1,700,000	£1,700,000	£1,700,000	£1,700,000	£1,660,000	£1,700,000					£600,000	£600,000	£600,000	£600,000	£600,000	£500,000	£600,000

		Total net benefits per year		-£800,000	£1,900,000	£3,600,000	£5,300,000	£7,000,000	£8,460,000	£8,460,000	£8,460,000	£8,460,000	£8,460,000	£8,500,000			£600,000	£1,200,000	£1,800,000	£2,400,000	£3,000,000	£2,900,000	£2,900,000	£2,900,000	£2,900,000	£2,900,000	£3,000,000
		Discount factor		100%	97%	93%	90%	87%	84%	81%	79%	76%	73%	71%			100%	97%	93%	90%	87%	84%	81%	79%	76%	73%	71%
		Discounted net benefits		-£800,000	£1,835,749	£3,360,639	£4,780,296	£6,100,096	£7,123,093	£6,882,215	£6,649,484	£6,424,622	£6,207,364	£6,025,810			£600,000	£1,159,420	£1,680,319	£2,164,662	£2,614,327	£2,441,722	£2,359,152	£2,279,374	£2,202,294	£2,127,820	£2,126,756

		Net Present Value	£54,589,367					£21,755,846

		Additional NPV for preferred option	£32,833,521

2) Incorporate into baseline
	Reframe all costs and benefits in terms of additional to the baseline
	So costs and benefits for our preferred option become:
			Preferred option vs Do Nothing baseline
			Total	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30
	Costs and benefits:
		Cost of lead development		-£1,000,000	£0	£0	£0	£0	£0	£0	£0	£0	£0	£0
	Per council:
		Cost of implementation		-£20,000	£0	£0	£0	£0	£0	£0	£0	£0	£0	£0
		Benefit of reduced licence fees		£0	£5,000	£5,000	£5,000	£5,000	£5,000	£5,000	£5,000	£5,000	£5,000	£5,000
		Benefit of reduced transaction costs		£0	£0	£0	£0	£0	£0	£0	£0	£0	£0	£0
		Benefit of higher transaction benefits		£0	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000	£50,000
		Renewal costs and benefits		£0	£0	£0	£0	£0	£3,000	£0	£0	£0	£0	£0
				-£20,000	£55,000	£55,000	£55,000	£55,000	£58,000	£55,000	£55,000	£55,000	£55,000	£55,000

	Councils adopting			20	20	20	20	20	0	0	0	0	0	0

	Cohort size	Y1		20	20	20	20	20	20	20	20	20	20	20
		Y2			20	20	20	20	20	20	20	20	20	20
		Y3				20	20	20	20	20	20	20	20	20
		Y4					20	20	20	20	20	20	20	20
		Y5					20	20	20	20	20	20	20
	Cohort net benefit
		Y1		-£400,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,160,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000
		Y2			-£400,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,160,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000
		Y3				-£400,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,160,000	£1,100,000	£1,100,000	£1,100,000
		Y4					-£400,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,160,000	£1,100,000	£1,100,000
		Y5					-£400,000	£1,100,000	£1,100,000	£1,100,000	£1,100,000	£1,160,000	£1,100,000

		Total net benefits per year		-£1,400,000	£700,000	£1,800,000	£2,900,000	£4,000,000	£5,560,000	£5,560,000	£5,560,000	£5,560,000	£5,560,000	£5,500,000
		Discount factor		100%	97%	93%	90%	87%	84%	81%	79%	76%	73%	71%
		Discounted net benefits		-£1,400,000	£676,329	£1,680,319	£2,615,634	£3,485,769	£4,681,371	£4,523,064	£4,370,110	£4,222,328	£4,079,544	£3,899,053

		Net Present Value	£32,833,521

	As this example shows, the NPV from both calculation methods is the same. You can select an approach that suits you.

## Detailed_working
IT system costs
CURRENT					NEW SYSTEM			COMPARISON

Strata costs (supporting 3 of the councils)					Local technical support (1 team per council)			Current cost per council	£265,019
	2018/19 costs	Projected 2019/20 costs	% of costs associated with Revs and Bens system	Total Annual Revs and Bens Costs		1x Engineer with DevOps skills	£52,610		New cost per council	£162,790
Infrastructure support					1x Support Engineer,	£42,140		Saving	£102,229
Staff Costs	£724,000	£738,480	15%	£110,772		1x Customer facing Service Owner / Project Manager	£47,430
Supplies and Services Costs	£830,301	£851,059	15%	£127,659		Total	£142,180
Business systems
Staff Costs	1,010,482	£1,030,692	15%	£154,604		Cloud hosting costs per council
Supplies and Services Costs	1,961,085	£2,010,112	20%	£402,022		1 x Database	£460
					4 x Application servers on two machines	£1,020
Total Strata revs & bens costs				£795,057		1 x Load balancer	£180
Per council (3 partners)				£265,019		Annual cost per council per year	£1,660
					Total for 5 partners	£8,300
Scaled current revs & bens running costs for all partners				£1,325,095
					Shared technical support to deliver the governance of the system
					Lead engineer	£52,610
					Support engineer	£42,140
					Annual cost per council per year	£94,750
Assumptions / - Current running costs have been based on the projected 2019/20 Strata IT support services model and scaled for 5 councils / - 2019/20 costs have been projected base on a 2.0% mark up on staff costs and a 2.5% mark up on supplies and services costs on 2018/19 actuals / - Infrastructure and Support: these costs are associated with the infrastructure and support (but excluding licencing and analysts) required to run the Revs and Bens system. It covers (but is not limited too) the costs of Data Centre, Network (MPLS), Servers, Storage, telephony required to run the Revs and Bens systems + the support resource required to design, build, test and run the infrastructure. / - Business Systems: these costs are associated with the Licencing costs (for all three councils) and Business Systems resource costs for running the Revs and Bens systems. It covers (but is not limited too) the costs of the relevant 3rd party licences + business analyst time to develop, test, implement and run the Revs and Bens systems + build integrations with other platforms. / - Scaling has been done as a multiple of 5 as Basildon and Brentwood are a joint service

					Total annual running costs for all partners	£813,950
					Annual running cost per council	£162,790

					Assumptions / - A multiple of 5 has been used for the totals for all partners as Basildon and Brentwood are a joint service / - role costs have been based on equivalent roles in the new Sedgemoor technical team / - Role costs include on-costs / - The shared central support costs may vary considerably depending on the governance model selected and as such may be significantly underestimated / - The shared central support costs could service up to approximately 10 councils and as such the annual running costs for each council may be achieved through these economies of scale / - As the partners onboard more councils a financial model could developed which reduces the annual running costs to provide a return on their investment in return for being the 'first movers'

Productivity
Current state for 6 councils
Total number of transactions per year	291256
Total number of FTE	191
No. of transactions per annum per staff member	1527
					Assumptions / - Information on volumes is based on data provided by Basildon, Brentwood & Teignbridge between the period 1st April 2018 and 31st March 2019 aggregated with estimates for Sedgemoor, Exeter and East Devon which are derived from the relative number of residential dwellings.
Opportunity calculations for 6 councils
	Low	High
Estimated inefficiency based on manual workarounds	6%	15%

Extra transactions that could be undertaken per year	17475	43688

Reduction in FTEs required to deliver the current levels of service	11	29
Estimated average salary with oncosts	£40,000	£40,000
Savings	£457,680	£1,144,200
Savings per council	£76,280	£190,700