Beta report
and next steps
Jason Tutin
Will Callaghan

---
In this report…
In this report…
Summary
Beta work
Research findings
Scaling the benefits
Direct impact on users
Next steps
Success criteria, risks and mitigations

---
Summary
Summary

---
Problem statement
Problem statement
How can we help councils
quickly develop effective digital inclusion programmes for their citizens, without them having to reinvent the wheel?

---
Summary
Summary
- Beta has given Digital Inclusion Toolkit strong foundations to build on
- 5 councils with advanced digital inclusion programmes are joining us
  - We intend to create a forum to discuss best practice and publish the results, benefiting all councils and their citizens
- We’re starting to see benefits to councils, and will make a concerted effort to collect meaningful data in the next phase
- Initial engagement with councils and on social media has shown a lot of interest, and there’s potential to grow our reach significantly

---
Beta work
Beta work

---
In Alpha we had to work at speed, quickly creating a website and publishing material at hand

---
Following your suggestion, we decided to include a lot more user research and reflection in the Beta

---
Research findings
Research findings
Blog post
Research report
[Speaker Notes: Over to Will - 9 to 17]

---
1
Focus on councils
In Alpha we spread ourselves too thinly by trying to provide content for councils, the third sector, healthcare providers and some direct advice for people who are digitally excluded. Our offer wasn’t detailed or useful enough
To get the most value, we decided to focus on councils as they often lead or coordinate digital inclusion for their geographical area

---
2
Help councils to get started
From our survey of 56 councils
62% trying to identify digitally excluded
76% identifying specific barriers
50% writing a strategy
44% securing investment
It’s clear that Covid-19 made digital inclusion a priority for councils. We decided to focus on content to help them get programmes started

---
3
The website needs an overhaul
Our content was well received and described as a useful set of resources. But there were challenges:
Useful advice buried in an unclear taxonomy
Too much case study content, not enough step by step ‘how to’ guides
Interest in ‘roundtable’ events to develop future content

---
Our research led to an overhaul of the site design, and we used the ‘innovation fund’ money to hire a content designer

---
Content design audit
Content design audit
See the full audit

---
New homepage and navigation
New homepage and navigation

---
Content rewritten as step by step ‘how to’ guides
Content rewritten as step by step ‘how to’ guides

---
Feedback suggests this is a huge improvement, and we will validate this with users
in the next phase

---
Scaling the benefits
Scaling the benefits

---
We asked councils with advanced digital inclusion programmes to join us and help create new material

---
We’re also talking to…
Current partners
Committed to joining in the next phase
We’re also talking to…

---
These organisations provide services for 16.3m people, of which 3.2m are likely to be digitally excluded

---
Norwich City Council
Dorset Council
“The toolkit is looking good.
We’re keen to support you to develop it further.”
Norwich City Council
“Yes, count us in!”

---
Greater Manchester Combined Authority
Greater Manchester Combined Authority
“I really like the toolkit, layout and everything.
“Very interested in seeing where it progresses, and how we can support you.”

---
SOCITM councils chose us as the home for all their digital inclusion research

---
Minutes from a SOCITM meeting attended by Calderdale, Croydon, Dorset, Kingston, Lancashire, London Borough of Barking and Dagenham, LOTI, Norwich, Oxfordshire, Royal Borough of Kensington and Chelsea
“The group agreed that considering the user feedback from councils about fragmentation of digital inclusion activity, it would be preferable to build on the existing MHCLG funded Digital Inclusion Kit, rather than creating a separate information source. The same applies to other research projects such as the one being led by Cheshire West and Chester Council on Understanding the Digital Divide.”

---
Direct impact on users
Direct impact on users

---
Our Theory of Change
has a comprehensive set
of metrics, but current data is mostly anecdotal
Read the Theory of Change

---
Project manager, East Sussex County Council
Project manager, East Sussex County Council
“I used the Digital Inclusion Kit to set up our IT For You At Home programme in April 2021. It was invaluable in working out our strategy and also deciding on operational and technical aspects.”

---
Unique users
Unique users
Digital Inclusion Toolkit will always be niche website, but we’ve shown it’s possible to drive meaningful traffic

---
Twitter activity
Twitter activity
When we use Twitter, we get engagement. In the next phase we intend to share new content every week

---
Next steps
Next steps

---
We want to involve
more councils, grow our reach, and explore ways to always deliver the best possible advice

---
1
Invite ‘mature’ councils to join us
Councils with advanced digital inclusion programmes have a wealth of best practice information to share, but nowhere to share it, or partners to discuss it with
We believe the Digital Inclusion Kit can grow a partnership of such councils, and publish the results. All councils will benefit, and so will the digitally excluded citizens they serve

---
2
Try roundtable discussions
During Alpha we talked about setting up regular video calls of councils with an advanced understanding of digital inclusion challenges
Each call would cover a specific issue
(eg measuring real world impact), and turned into guidance for the Digital Inclusion Kit
We intend to try a couple of roundtables in the next phase of work, iterating as needed

---
3
Validate Beta work
Backed by Beta user research findings, we made major changes to the design and content of the Digital Inclusion Kit
It’s time to go back to councils who took part in the last round of research, and to new ones, and find out what they think. We expect to find gaps in our current content and the need to make further changes to the site functionality

---
4
Start collecting meaningful data
Our Theory of Change includes useful metrics,
but it’s been too early in our development to benchmark the effect of our work on councils and their digitally excluded citizens
Now we have stronger foundations, we will make a concerted effort in the next phase to involve more councils, and ask for evidence of impact

---
5
Grow our social media reach
At intervals during Beta we tried growing our Twitter reach
Ensuring we always had high quality advice to publish and share
Taking part in relevant Twitter conversations
Our followers increased to 225, and we saw similar increases in reach, page visits and time on our site. Based on the experience of LocalGov Drupal, we think it’s possible to double our current reach

---
We believe the extra collaboration will open up many more opportunities, and we plan to approach the Local Digital Fund again

---
Success criteria,
risks and mitigations
Success criteria,
risks and mitigations

---
What success looks like
What success looks like
Digital Inclusion Kit is early in its journey, but we expect to see changes to these metrics over the course of the next phase
Metric	Target
Number of councils collaborating on the Digital Inclusion Kit	5 councils with advanced programmes
Number of councils who’ve seen our advice	50
Councils seeing us as an expert in digital inclusion	25
Councils able to start or accelerate activities based on our advice	10
Councils unlocking funding based on our advice	No target, but will report results of working with a small number of councils
Councils trying more innovative approaches based on our advice	No target, but will report results of working with a small number of councils
Return on investment for councils	Let’s discuss at the interview!

---
Risks and mitigations
Risks and mitigations
Councils have realised that digital inclusion work is vital, but they don’t necessarily have internal buy in to be effective
Risk	Mitigation
Content or site features don’t meet common needs	Further user research will inform our development, with regular reviews to ensure we always respond to common needs
Internal pressures mean that councils can’t act on our advice	Understand more about the pressures, and write articles to explain how digital inclusion can help to alleviate them
Low levels of awareness and engagement from councils	Participating councils create and share content via their social media and local networks
Too difficult to quantify time and cost savings for councils using the Toolkit	Work more closely with some councils and collect regular feedback from the start of their Toolkit journey
Participating councils don’t see any benefit from their involvement and disengage	Ensure the Roundtables add value for participating councils by informing and shaping their digital inclusion programmes

---
2021 Queen’s Speech
2021 Queen’s Speech
The government will… “level up opportunities across all parts of the United Kingdom, supporting jobs, businesses and economic growth and addressing the impact of the pandemic on public services”

---
Councils we speak to
increasingly see digital inclusion work as an essential part of levelling up

---
Any questions?
Web	digitalinclusionkit.org
Twitter	@diginclusionkit