## Slide 1: Unpaid Carer Discovery Research plan

## Slide 2: Content
Research scope, goals and objectives
Target audience and sample size
Research method and recruitment
Research timeline and deliverables
Key research questions
  Adult carers
  Young carers
  Carer organisation leads/network
Reference: Plan user research for your service - GOV.UK

## Slide 3: Research scope, goals and objectives
✅Conduct a series of user research activities to uncover the needs of unpaid carers in SEL, with regards to accessing and using digital services/online resources
✅Provide a landscape mapping of existing support
Research objectives
(measurable actions)
Scope
✅Unpaid carers in SEL, including adult and young carers of different characteristics
✅Carer organisations in SEL, who provides support to unpaid carers
✅Carers experience relate to accessing and using digital service and online resources
❌ (Not in scope) General carer challenges that are not possible to resolve within this project. For example, improve mental health support. If this comes up as a key need from carers, we will note down and refer it to other responsible teams.
Overall aim
✅Determine how a new or improved digital offer can respond to carer needs, and help unpaid carers across SEL better access and use relevant information, advice and support

## Slide 4: Target audience
33
Adult carers
1:1 interviews
Local carer’s events
2
events
Meeting carers support networks
5
VCS
3
Other groups
All boroughs involved
Carer sub-types
Reasons for providing care to someone
Different age groups
Inclusive research
Digital maturity
English as a second language
Culture preference
Protected characteristics
Different type of support
Desired format and sample size
10
Young
carers
Who
Individuals caring for people, outside of being formally employed as a carer. We would like to research with carers from a diverse background to understand various experiences, and networks and organisations that support them. Please refer to the sample slide for more details.

## Slide 5: Sample size and composition in all involved boroughs
Borough | Number of unpaid carers* | Of which young carers*(c.3%) | Desired sample Adult carer | Desired sample Young carer | Sample composition notes
Southwark | 37,635 | 1,170 | 6 | 2 | Among adult carers, please aim to identify a diverse group of users we can speak to: Different age group (<30, 30-60, >60) Different ethnicity (White, Black, Asian, mixed, multiple etc) Different number of hours they provide unpaid care (<19 hours, 20-50, >50 hrs) Different reasons for caring for someone (disability, age, mental illness, addition…) Culture background/Country of origin Annual Income level, if applicable(<30K, 30-60K, >60K) Different levels of digital maturity Among young carers, please include: Different number of hours they provide unpaid care (<19 hours, 20-50, >50 hrs) Different reasons for caring for someone (disability, age, mental illness, addition…) Culture background/Country of origin
Bromley | 50,745 | 1,265 | 7 | 2 | 
Lambeth | 37,705 | 1,185 | 6 | 2 | 
Bexley | 38,555 | 915 | 6 | 2 | 
Greenwich | 38,790 | 1,110 | 6 | 2 | 
Final sample (43 total) |  |  | 33 | 10 | 
Source of data: Unpaid care, England and Wales: Census 2021

## Slide 6: Research method and recruitment approach
1:1 interview
Carers local events
Survey
Workshop
The PSC role | Organiser, interviewer | Participant, observer | Creator, analyser | Organiser, facilitator
Method description | [Phase 1] In-depth face to face (physical or virtual) interview (45 mins) to ask research questions and gain understandings | [Phase 1] Face to face events to talk to carers in a more casual setting, gain insights and observe existing forms | [Phase 1] Digital survey, including an easy read version, to be sent to carers via VCS groups to provide supplementary insights | [Phase 3 only] face to face workshops to co-design support solutions, 1 with carers and 1 with borough leads
Rationale | Main form of understanding through conversations to ensure we know the insights and the rationales | Engage with carers in short conversations to gain insights and to meet them where they are more comfortable | Supportive understanding for those we are not able to engage due to time and budget limit | To have focused time together to design and test potential solutions (e.g., a virtual carers hub)
Recruitment strategy | Borough leads link with existing networks Newsletter | Carer organisations Borough leads | Distribute through care networks existing carers contact bank | Borough leads Phase 1 interviews
1:1 interviews are compensated with £20/person in the format of a shopping voucher or charity donation

## Slide 7: Overall project timeline for reference
3. Design solution
2. Define needs
Discover experience
4. Deliver Final report
 | W0 11/12 |  | W1 01/01 | W2 08/01 | W3 15/01 | W4 22/01 | W5 29/01 | W6 05/02 | W7 12/02 | W8 19/02 | W9 26/02 | W10 04/03 | W11 11/03
Work stream |  | Holiday Closure |  |  |  |  |  |  |  |  |  |  | 
Kick-off
Show & Tell 1
Co- design workshops
Final
S&T
S&T 2
Handover
Kick off
Research plan
Unpaid carer research and engagement
Holistic service/support mapping
Market/best practice research
Carer needs synthesise
Design VCH and prototype
Carer testing
Refinement designs
Refinement workshop
Road maps and final report
Doc review
Arrange meetings
User recruitment
Carer needs prioritise
Borough leads engagement

## Slide 8: Research timeline and deliverables
Week | W1 01/01 | W2 08/01 | W3 15/01 | W4 22/01 | W5 29/01 | W6 05/02
Workstream |  |  |  |  |  | 
Desired outputs | User engagement brief Survey draft Borough leads reached out | List of unpaid carers obtained Interview guide confirmed Survey distributed | Interview notes Events scheduled to join Initial interviews | Survey analysis Preliminary network and local carer event findings/summary | Synthesised user engagement findings | User journey maps and personas Service provision maps
Key Meetings | Weekly update meeting (Thursday) | Weekly update meeting (Thursday) | Weekly update meeting (Thursday) | Thursday January 25th 10 am: Show & Tell | Weekly update meeting (Thursday) | Weekly update meeting (Thursday)
User research (1:1 interview) - unpaid carers
Carer orgs/groups
Attend local carer’s events
Continuous recruitment
Holistic service/support mapping/synthesising
Survey design
Research plan and interview guide
Survey distribution
Recruitment
Research
Analysis
Synthesise, insights and artefacts drafting

## Slide 9: Interview guides for review

## Slide 10: Key research questions - Adult carer (1/2)
Intro
Who you are
Why are you caring for someone? How many hours roughly do you care for someone per week?
How long have you been caring for them? When did you start to think of yourself as a carer?
If you were a carer from a young age, how did you find the transition from a young carer to an adult carer?
Awareness of digital support and online resources (advice, information)
Have you searched for support online? What made you want to look for support and advice online?
How often do you look for support or information online?
If not, or use the internet not very much, how do you find the information you need for you and for the person you care for?
What do you type in or look for when you are looking online for carer information? What do you think you or other unpaid carers google the most? (think about the last 3-5 times you searched for something)
How did you know about the services you’ve searched for? Did someone help you or tell you about online support?
What do you use to look things up (mobile device, computer, etc.)?
How happy are you with online services that support you as a carer? (1-10)
How happy are you with general services that support you as a carer? (1-10)
Experience with searching online resources and using digital services
Was the information you found helpful? Is it up to date?
What sections of the council website or other carers website you normally go to? (The adult carer section?)
How you these websites compare to others you use? Are they easy to use/move around?
What websites do you trust for information about caring?
Adult carer
Young carer
Carer organisation leads
45 mins virtual or face to face interview

## Slide 11: Key research questions - Adult carer (2/2)
Needs and pain points with accessing advice, information and support online
How well do the services or resources help you take care of yourself?
How well do the services or resources support you help you care better?
What has not worked well when you’ve tried to access information or services online (eg. information not up to date, unclear language, unclear who it is for?) Think about an instance where it didn’t work well, what happened?
Have you been able to use, or would want to use, a website or online resource to connect with other carers like yourself?
Improvements:
How can we better support you as an unpaid carer and the person you care for, in a digital way?
How can we better support you outside of your identity as a carer?
What would make it easier for you to access information or advice online?
How can we make that digital offer most effective, for people like you?
How would you want to be able to provide feedback to continually improve the service?
Adult carer
Young carer
Carer organisation leads

## Slide 12: Key research questions - Young carer (1/2)
Intro
Who you are
Why are you caring for someone? How many hours roughly do you care for someone per week?
How long have you been caring for them? When did you start to think of yourself as a carer?
Awareness of digital support and online resources (advice, information)
Have you searched for support online? What made you want to look for support and advice online?
How often do you look for support or information online?
What do you type in or look for when you are looking online for carer information? What do you think you or other unpaid carers google the most? (think about the last 3-5 times you searched for something)
How did you know about the services you’ve searched for? Did someone help you or tell you about online support?
What do you use to look things up (mobile device, computer, etc.)?
How happy are you with online services that support you as a carer? (1-10)
How happy are you with general services that support you as a carer? (1-10)
Experience with searching online resources and using digital services
Was the information you found helpful? Is it up to date?
Do you only look at young carer sections of these sites or also at the adult carer sections? Is there info in the adult carer sections that you think is helpful?
How you these websites compare to others you use? Are they easy to use/move around?
What websites do you trust for information about caring?
Adult carer
Young carer
Carer organisation leads
Questions marked red are young carer specific questions
45 mins virtual or face to face interview

## Slide 13: Key research questions - Young carer (1/2)
Needs and pain points with accessing advice, information and support online
How well do the services or resources help you take care of yourself?
How well do the services or resources support you help you care better?
Do they help you with things that you might be too young to help out with (like driving someone somewhere or pick up prescriptions)?
Do you have access to the devices you need to use these websites or services (like a phone or tablet)?
What has not worked well when you’ve tried to access information or services online (eg. information not up to date, unclear language, unclear who it is for?) Think about an instance where it didn’t work well, what happened?
Have you been able to use, or would want to use, a website or online resource to connect with other carers like yourself?
Improvements:
How can we better support you as an unpaid carer and the person you care for, in a digital way?
How can we better support you outside of your identity as a carer, and help you grow as a young person?
What would make it easier for you to access information or advice online?
How can we make that digital offer most effective, for people like you?
How would you want to be able to provide feedback to continually improve the service?
Questions marked red are young carer specific questions
Adult carer
Young carer
Carer organisation leads

## Slide 14: Key questions - carer organisation leads
Intro:
Does the organisation have a particular focus (ie. in the individuals it provides services or select services)?
Digital Support:
What is the current digital offer?
Does the organisation have any plans to bolster their digital services? Specific areas or tools they’re looking to offer in the future?
Does the network or organisation offer any online tools (eg. an online directory, online meetings, or virtual forums for carers to connect)?
Does the organisation collaborate with other organisations in the area or have a joint digital offer?
What are the services or challenges that unpaid carers facing can be solved/supported digitally?
Does the organisation have any ideas as to what carers are looking for in a digital service?
Carers’ access
How does the organisation promote itself? Are there campaigns or outreach measures taken?
How do carers come to learn about the service?
Carers’ experience and usability
Has the organisation received any feedback for carers regarding their digital offering or services?
How does the organisation feel is the general usability or effectiveness of their digital services?
Are there particular digital offerings that are well used or under used?
Are there any key learnings around implementing a digital service?
Benefits and challenges
Are there any insights into the benefits of specific services relatively to the cost of the service?
What are the key challenges and blockers to offering a digital service?
Adult carer
Young carer
Carer organisation leads
30-45 mins virtual interview
Notes: Purpose:
Understanding the online tools of the organisation
How the organisation or network promotes itself
Is the organisation or network linked into to the council website or other online directories
How carers have responded or taken up some digital tools (if any)